## Tools-Job Load(FY 2026-2027)
[15 empty] | 2026-04-01 | [29 empty] | 2026-05-01 | [30 empty] | 2026-06-01 | [29 empty] | 2026-07-01 | [30 empty] | 2026-08-01 | [30 empty] | 2026-09-01 | [29 empty] | 2026-10-01 | [30 empty] | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01
|  |  | Released | ○ |  | Members shared |  | Other Team ID Creation |  | Effort 9MH / Per day calculation done |  | Updated Order List Effort Modified ( Loading refreence Purpose) | [337 empty] | 2027-03-01
|  |  | YTS | × |  |  |  | Approximation load (need to confirm) |  | Effort Not confirmed |  | Job Hold
|  |  | WIP | ▲ |  |  |  | Effort Modified |  | YTS
No. | Project ID | Project Name | Project Type | Leads | Team Members | Salesforce Effort/Internal Effort(MH) | Tools Team Commit Effort (MH) | Job Order NO. | Project Team | Start Date | Release Date | Remarks | Language | Job Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | CS753AC | SRMT-xxxxx-Autograph Tool-v1.1 | Client | SR | PS | 65 | 45 |  | SVAT | 2026-02-23 | - | Requirement Analysis | Python | ○ | bar: 1 to 8; 11 to 12; 14; 19; 23; 25 to 26; 1 to 3; 9 to 10; 16 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
2 | CS753AA | TAS_TOOL_VER_2.1 | In-house | SR | PS |  | 27 |  | PMO | 2026-02-27 |  |  | VBA | ○ | bar: 3 to 5; 11 to 12; 14; 19; 23; 25 to 26; 1 to 3; 9 to 13; 16 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
3 | CS753AB | Outlook_Configuration_Tool | In-house | SR | SG |  | 27 |  | PMO | 2026-02-17 | - |  | Python | ○ | bar: 3 to 5; 11 to 12; 14; 19 to 23; 25 to 26; 1 to 3; 9 to 10; 16 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
4 | CS753AE | RAM_ROM_Memory_Calculation_Tool | In-house | SR | YS | 65 | 31.5 |  | SVAT | 2026-03-17 | 2026-03-31 |  | C# | ○ | 1: 1; 2: 1; 6: 0.5; 7: 0.5; 8: 0.5
5 | CS767G | NPCU Regression Testing Execution Tool | Client | SR | SR, SU | 490 | 432.45 |  | SVAT |  |  | 490 hrs effort shared in order 875668 PJ117 B NISSAN FACE-PCU 2025_Q4 | Python | ▲ | 6: 1.5; 7: 1.5; 8: 1.5; 9: 1.5; 10: 1.5; 13: 1.5; 15: 1.5; 16: 1.5; 17: 1.5; 18: 1.5; 20: 1.5; 21: 1.5; 22: 1.5; 24: 0.75; 27: 1.5; 28: 1.5; 29: 1.5; 30: 1.5; 4: 1.5; 5: 1.5; 6: 1.5; 7: 1.5; 8: 1.5; 11: 0.8; 12: 1.5; 13: 1.5; 14: 1.5; 15: 1.5; 18: 1.5; 19: 1.5; 20: 1.5; 21: 1.5; 22: 1.5
6 | CS767H | GUNMA_IH_SD_Automation_Tool | In-house | SR | YS,PS | 520 | 192.6 |  | RE-DEV | 2026-04-07 | 2026-04-17 | Tool was hold due to estimation confirmation. | C# | ▲ | 8: 0.5; 9: 1.5; 10: 1.5; 13: 1.5; 15: 1; 16: 1.5; 17: 1.5; 18: 1.5; 20: 1.5; 21: 1.5; 22: 0.5; 24: 0.7; 5: 0.5; 6: 1; 18: 0.5; 19: 1.4; 20: 1.4; 21: 0.5; 22: 1.4
7 | CS767I | GUNMA_IH_CAN FD macro-v1.1 | In-house | SR | SG | 36 | 36 |  | RE-KEN | 2026-04-15 | 2026-04-30 |  | VBA | ○ | bar: 3 to 5; 11 to 12; 14 to 19; 23; 25 to 26; 1 to 3; 9 to 10; 16 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
8 | CS767J | ADAS_IH_SDS_Tool | In-house | SR | YS | 40 | 45 |  | ADAS | 2026-04-27 | 2026-05-11 |  | VBA | ○ | 24: 0.5; 27: 1; 28: 1; 30: 1; 4: 0.5; 5: 0.5; 6: 0.5
9 | CS767K | MASTA_IH_RAM_Configuration_Support_Tool | In-house | SR | PS, SG |  | 90 |  | MASTA | 2026-04-24 | 2026-05-11 |  | VBA | ○ | bar: 3 to 5; 11 to 12; 14; 19; 23 to 10; 16 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
10 | - | NEW TOOL Autograph | Client | SR | PS |  | 28.8 |  | SVAT | 2026-04-22 | - |  | Python | ▲ | 22: 0.5; 27: 0.5; 28: 0.5; 4: 0.7; 5: 1
11 | CS767L | Outlook_Cofiguration_Tool-V1.01 | In-House | SR | SG |  | 63 |  | PMO | 2026-05-07 | 2026-05-15 |  | Python | ○ | bar: 3 to 5; 11 to 12; 14; 19; 23; 25 to 26; 1 to 3; 7 to 17; 23 to 24; 30 to 1; 7 to 8; 14 to 15; 21 to 22; 28 to 29; 5 to 6; 12 to 13; 19 to 20; 26 to 27; 2 to 3; 9 to 10; 15 to 17; 23 to 24; 30 to 31; 5 to 7; 13 to 14; 20 to 21; 27 to 28; 1 to 2; 4 to 5; 11 to 12; 18 to 20; 25 to 26; 1 to 2; 8 to 9; 15 to 16; 22 to 23; 29 to 30; 6 to 7; 13 to 14; 20 to 21; 25; 27 to 28; 1; 3 to 4; 10 to 11; 15 to 18; 24 to 26; 31 to 1; 7 to 8; 14 to 15; 21 to 22; 28
12 | CS767N | Status Mail Report Tracking Tool | In-House | SR | SG |  | 4.5 |  | PMO | 2026-05-07 | 2026-05-15 | Hold due to Sundar G is supporting to Dev ST (19-05-2026). | Python | ▲ | 18: 0.5
[6 empty] | 1176 | 791.55 | [7 empty] | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 3.5 | 3 | 3 | 0 | 0 | 3 | 0 | 2.5 | 3 | 3 | 3 | 0 | 4 | 4 | 3.5 | 0 | 2.95 | 0 | 0 | 4 | 4 | 2.5 | 3.5 | 0 | 0 | 0 | 3.7 | 4.5 | 4 | 3.5 | 3.5 | 0 | 0 | 2.8 | 3.5 | 3.5 | 2.5 | 2.5 | 0 | 0 | 2.5 | 2.9 | 2.9 | 2 | 2.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Month | SVAT Jobs Count | ADAS Jobs Count | AD Tech Jobs Count | COE Jobs Count | GUNMA Jobs Count | HASA Jobs Count | MASTA Jobs Count | MBD Jobs Count | PMO Jobs Count | KENSHOU Jobs Count
2026-04-01 | 2 | [7 empty] | 1 | 1
2026-05-01 |  | 1 |  |  |  |  | 1 |  | 1
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
Total | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1
Month | MIN Load Reach | MAX Load Reach | Release Count | Month | Average Load / Day
2025-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2025-11-01
2025-12-01
2026-01-01
2026-02-01
2026-03-01
|  |  | #DIV/0! | AVERAGE
Note on L11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Tool Requirement Analysis start date
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Tool Requirement Analysis start date
Note on L13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Tool Requirement Analysis start date
Note on L14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Tool Requirement Analysis start date

## Month_Wise_Effort (hidden)
2025-04-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS713AB | COE | Internal | AD_(In-House)ENG_CAPL_GenTool-Analysis] | SK | 459
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS713BA | ADAS-BSW | Client | CAN-Prerequest Tool | YS | 203.04
2025-05-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS753F | ADAS | Internal | CCS_Code_Tool | SR | 203.04
2025-05-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS753J | ADAS | Internal | CAN_MessageList _Diff_Tool | YS | 70
2025-06-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS753Ｋ | ADAS | Internal | CAN_MessageList _Diff_Tool_V3.0 | YS | 70
2025-06-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS753L | HASG | Internal | XREF- Read_Write updation Tool | YS | 48
2025-06-01
S.NO | PROJECT ID | Team | Client/ Internal | Project Name | Member | Effort
1 | CS753N | HASG | Internal | Grep_Doc_Tool | YS | 48